# Restaurant System Conversion

Phase 2 Support

12/4/2025

Contents

Problem Statement	3

Current State	3

Desired State	3

Remaining Scope of Work	4

Franchise Group Contacts (to be verified)	4

System Integrations (to be verified)	4

Proposed Approach	6

HCSS General Role/Responsibilities	6

The purpose of this document is to revisit the project status based on the Fall 2025 rollout status and suggest changes for the remainder of the rollout.

# Problem Statement

## Current State

- The Crunchtime and Toast systems have been rolled out to 1 of the 13 franchise groups from 10/ to 11/19/25.

- Fridays, Crunchtime, and Toast have struggled to deliver the rollout to the Sugarloaf franchisee in an organized/effective manner.

- The timeline was aggressive, and the time needed for testing was nonexistent.

- Training and communication were fragmented and unorganized.

- Fridays IT resources were stressed to learn the new system and support the needed configuration and manage hardware/support logistics.

- The contract process was cumbersome.

- Issue reporting and management have been fragmented.

- The franchise group management had post-rollout concerns and needed remedial training.

## Desired State

- Apply learnings from the Sugarloaf restaurant rollout to the remainder of the franchisee groups.

- The remaining franchisee groups have a point person to help them through their rollout. This will include helping them understand the process, assisting with contract signatures, coordinating site surveys, hardware logistics, training, communication, and escalation needs.

- The remaining franchisee groups:

  - Received timely communication about the system rollout.

  - Have been effectively trained and have the resources to do their job on the new system.

  - The rollout did not disrupt their business.

- The Friday’s project team is operating in a more streamlined approach regarding rollout details tracking, issue management, and work meetings.

- The remainder of the rollout:

  - is managed by a better-trained support team

  - supports a better tested franchise group-specific configuration

  - allows for a more prepared support and operational team

- See the recommendations section for more details.

# Remaining Scope of Work

- 12 more franchise groups and 70-80 more restaurants will need to be rolled out (see list below).

- Work to roll out each one will include:

- Onboarding and contract signatures

- Site Survey and hardware orders/installation

- Franchise group-specific configuration

- Franchise group-specific system interface planning, development, and testing (see list below).

- Communication, training, and onsite support planning & execution

- Stabilize

## Franchise Group Contacts (to be verified)

| Franchise Group | Contact | Email | Phone | Locs |
| --- | --- | --- | --- | --- |
| American Pub | Kishan Patel | kishan@americanpub.us | (909) 264-1550 | 2 |
| Bridgeport Restaurant Group | John Mosesso | jmoerentals@frontier.com | (304) 203-4172 | 1 |
| Cedar Fair | TBD | TBD | TBD | 1 |
| CFC Stripes | Jill Cygan | jcygan@cfcmgmt.com | (216) 328-1121 | 2 |
| Jackmont Hospitality | Daniel Halpern | dhalpern@jackmont.com | (404) 523-5744 | 21 |
| Maui One | Anil Yadav | anil@yadavgroup.net | (510) 792-2628 | 28 |
| Mera | Rafael Aguirre | rafaelat@meracorporation.com | +52 (998) 845-6064 | 5 |
| Metz Culinary | Jeff Metz | jeffm@metzcorp.com | (570) 674-8731 | 7 |
| RLJ Development | Eric Rogers | erogers@rljlodgingtrust.com | (301) 280-7754 | 1 |
| United Restaurant Group | Tony Grillo | tgrillo@atlanticcoastdining.com | (804) 747-5050 | 9 |
| Village XIII | Dale Holt | dholt44@sbcglobal.net | (217) 356-5789 | 1 |
| VNE | Jeremy Gardner | jgardnermail@gmail.com | (501) 472-1000 | 2 |

## System Integrations (to be verified)

| Franchise Group | Category | System |
| --- | --- | --- |
| American Pub LLC | Accounting | InfoSync |
| American Pub LLC | Labor/ Payroll | InfoSync |
| Bridgeport | Labor/ Payroll | InProcess Company |
| Bridgeport Restaurant Group | Accounting | InProcess Company |
| Cedar Fair L.P. (via NCR/Micros upload) | Accounting | J.D. Edwards |
| Cedar Fair, RLJ Development | Labor/ Payroll | Kronos / UKG |
| CFC Stripes | Accounting | Restaurant 365 |
| CFC Stripes | Labor/ Payroll | MinuteMen HR |
| Jackmont | Accounting | Great Plains |
| Maui One, Mera | Accounting | Sage Intacct |
| Mera (effective 8.12.25) | Labor/ Payroll | UKG |
| Metz Culinary Management | Accounting | Business Central |
| United Restaurant Group L.P. | Accounting | Sage 100 ERP |
| United Restaurant Group L.P. | Labor/ Payroll | Paycom |
| Village XIII | Labor/ Payroll | Custom Computing Inc |
| Village XIII, VNE Inc. | Accounting | QuickBooks |
| VNE Inc. | Labor/ Payroll | Paychex PEO |

## Recommendations

The following table outlines recommendations for improved project workflow and effectiveness.

| Recommendation | Notes |
| --- | --- |
| - Create Playbook for Remaining Franchisees | Example Sections - Process (contract signed, site survey, hardware, training, rollout) - Suggested communication - Suggested training kit - Key learnings from SugarLoaf Restaurant rollout |
| - Formalize Franchisee Onboarding Process (starting now) | - Formal Kickoff Meeting with Each Franchisee - Contracts - Restaurant Site Surveys - Assess cultural/organizational needs - Provide Playbook - Integration Assessment – review system integration needs / nuances/outliers |
| - Institute Master Rollout Tracking | Expand on the one Eddie and Mario have been using. Create individual worksheets for the below with designated owners for each tab. Examples: - Master Rollout Schedule by Restaurant - Site Survey Hardware tracking - On-site installation support - Toast configuration/integration milestones by restaurant - CT configuration/integration milestones by restaurant One location for CT, Toast, and Fridays to access |
| - Enhanced Issue Management | Better organize issues for reporting, resolution, and learning. Examples: - All issues/questions should be sent to IT help desk. This includes restaurants, internal departments, and franchisees. - If there are any issues received outside of this flow, the sender should receive a confirmation of receipt with a note about future emails to be routed to the IT. The IT help desk should be copied on this confirmation email. - If it doesn’t feel appropriate for some people (executives, internal departments, etc.) to contact IT helpdesk, then perhaps another email distribution group could be created for this: (NewSystemExecSupport@fridays.com) - Need good governance (for content, triage, reporting, resolution) |
| - Restructure Project Meeting Cadence | Change/institute new meetings with clear agendas. Suggestions: - Bi-weekly CT work sessions - Bi-weekly Toast work sessions - Weekly joint CT/Toast meeting - Weekly internal project meeting - Franchisee specific (as needed) |

# Proposed Approach

HCSS will facilitate and coordinate the activities necessary to execute the recommendations.  Standard process and project management techniques/roles will be used.  The project owners will direct HCSS.

## HCSS General Role/Responsibilities

Coordinate between 3rd parties and TGI Fridays workstreams/functions to keep the project on track. This will include normal project management activities and these specifics:

- Facilitate Franchise group onboarding and liaison activities

- Governance and support of master rollout tracking

- Status/Issue reporting

- Risk/issue management and escalation

- Meeting facilitations

- Support for change management (communication, training, post-go-live support, etc.).

- Assist where needed on configuration, data analysis, and testing.